## RAID
Category | ID | Title | Description | Severity | Owner | Mitigation | Due
Risk | R1 | Third-party API Integration Delay | Potential delays in integrating the Google authentication API could push back the timeline. | High | Backend Developer | Start integration early and maintain close communication with API providers.
Risk | R2 | Limited API Access | Constraints on API access may limit the functionality or speed of development. | Medium | Backend Developer | Identify specific access limitations early and request necessary permissions from the client.
Assumption | A1 | Timely Credential Provision | Assumption that the client will provide necessary API keys and credentials by the agreed deadline. | Low | Client | validate assumption | 2026-04-11
Assumption | A2 | Scope Stability | Assumption that the requirements for login and dashboard analytics remain unchanged for the 2-week duration. | Low | Project Manager | validate assumption
Issue | I1 | API Key Pending | Client has not yet provided the API keys required for the backend team to begin integration. | Medium | Client | Follow up with client immediately to secure keys by tomorrow. | 2026-04-11
Issue | I2 | Tight Timeline | The 2-week timeline is aggressive given the API dependencies and design requirements. | Medium | Project Manager | Parallelize UI design and API design tasks to maximize efficiency.
Dependency | D1 | Google Authentication API | The login module depends on the successful integration of the Google authentication service. | High | Backend Developer | Develop a fallback local authentication method if Google API is unavailable.
Dependency | D2 | Third-party Auth Services | Overall project delivery is dependent on the availability and stability of third-party authentication services. | Medium | Backend Developer | Implement robust error handling for third-party service outages.