## RAID
Category | ID | Title | Description | Severity | Owner | Mitigation | Due
Risk | R1 | Schedule slip | Derived from inputs; confirm timeline. | Medium | PM | Re-baseline plan and escalate early.
Assumption | A1 | Stakeholder availability | Key reviewers available for sign-off windows. | Low | PM | Book reviews in advance.
Issue | I1 | Open integration dependency | Third-party API contract not finalized. | High | Tech Lead | Timebox vendor alignment workshop.
Dependency | D1 | Infrastructure readiness | Cloud tenancy and access controls. | Medium | Ops | Track in weekly RAID review.