## RAID
Category | ID | Title | Description | Severity | Owner | Mitigation | Due
Risk | R1 | Third-party API Integration Delay | Potential delays in integrating the Google authentication API could push back the timeline. | High | Backend Developer | Start integration early and maintain close communication with API provider support. | 2026-04-13
Risk | R2 | Limited API Access | Constraints on API access may limit the functionality or speed of development. | Medium | Backend Developer | Identify all required endpoints early and request full access permissions immediately. | 2026-04-11
Assumption | A1 | Timely Credential Provision | Assumption that the client will provide necessary API keys and credentials by the agreed date. | Low | Project Manager | validate assumption | 2026-04-11
Assumption | A2 | Scope Stability | Assumption that the requirements for login and dashboard analytics remain unchanged for the 2-week duration. | Low | Project Manager | validate assumption | 2026-04-10
Issue | I1 | Pending API Keys | Client has not yet provided the API keys required for the backend team to start integration. | Medium | Client | Follow up with client to ensure delivery by tomorrow. | 2026-04-11
Issue | I2 | Tight Timeline | The 2-week timeline is aggressive given the API constraints and design requirements. | Medium | Project Manager | Parallelize UI design and API design phases. | 2026-04-10
Dependency | D1 | Google Authentication API | The login module is dependent on the successful integration of the Google authentication service. | High | Backend Developer | Develop a mock authentication service for frontend development while API is pending. | 2026-04-13
Dependency | D2 | Third-party Auth Services | Overall project delivery depends on the availability and stability of third-party authentication services. | Medium | Backend Developer | Implement robust error handling for third-party service outages. | 2026-04-24